## Slide 1: HPRS Health Patient Registration System

## Slide 2: Objectives
What is the Purpose?
High level overview of the system
Detailed Status in Gauteng
How it is currently working/not working in Gauteng?
What are the Challenges?
Objectives of the Aurum Strategic Project
Next steps

## Slide 3: eHealth Strategy
The eHealth Strategy for South Africa is a roadmap for achieving a well-functioning, patient-centred electronic national health information system.
Integrated national patient-based information system
Interoperability towards improving the efficiency of clinical care, producing the indicators required by management, and facilitating patient mobility.
All patient-based systems will be linked to a national electronic health record repository, thereby supporting access by all facilities to all records at all other facilities.
As such, all routine public health data will be derived from patient data captured electronically at the point of care.

## Slide 4: The Building Blocks of the eHealth Strategy
The primary objective of the first version of the strategy was to set the foundational basis for interoperability in national healthcare information systems.
The Green Paper for National Health Insurance in South Africa identified the need for a patient registration system, so as to plan the provision of healthcare facilities and services as well as support tracking the usage of health services.
The requirement were:
  Patient indexing capabilities for electronic health records.
  Patient Registry and Master Patient Index service using the South African Identification Number and all other legal personal identification numbers (e.g. the passport number) as the primary patient identifier, making it possible to track patients at all levels of care for improving quality and continuity of care.
  Description of the enterprise architecture Health Information is captured and required for different purposes at different levels of the health system.
  Co-ordinate the exchange of health information data, it was imperative to design a framework within which the different information systems and data repositories interact in a standardised manner.
  The architecture of a fully integrated national shared electronic health record.

## Slide 5: Where does HPRS fit in?
In July 2013 the National Department of Health contracted the CSIR for the development of
an Health Patient Registration System (HPRS). This system standardise patient registration
across all health facilities, using the SA Identity Number as a unique patient identifier.
It supports the tracking of utilisation and linkage to electronic health records. The purpose is
to create a register of patients, to assist the health sector with planning and improved service
delivery. It further tracks the beneficiaries accessing services at health facilities at different
levels of care.
The software development of the system has completed version 0.1.3 and the current
system capabilities are:
  • Barcode Scanning (ID Book and Driver’s License) and Biometric reader
  • Patient lookup (patient demographic details, facility linkage, patient file number)
  • Generate a patient file number
  • Maintenance of patient details
  • Linkage of patient to PHC facility
  • Record the visit (date, time, facility, purpose)
  • Management information – health service provision

## Slide 6: High Level Overview
Verify the identity of each patient that visits a health facility.
Identity verification of patients should be performed, when possible, with the assistance of the DHA’s Home Affairs National Identification System (HANIS).
Visual verification of a patient’s identity will also be performed whenever a valid identification document is presented.
Register a patient on the system in order to manage all available identification and geographic information of the patient.
Update the information for an existing patient that was previously registered.
Record all visits to the health facility.
Schedule appointments for patients at the facility.
Print personalised patient labels for use on paperwork and test requests / results.
Generate various system reports to assist the NDoH with the effective planning for and provisioning of health care facilities.

## Slide 7: Filing System Benefits
Automatically generates a patient record number
Links unique identifier to patient record
Automatically incorporates the position of the patient records on the filing cabinet into the record number
Allows for rapid retrieval of files
Provides a common filing language
Adaptable to different size of filing cabinets

## Slide 8: Implementation Process Based on Maturity Levels
Maturity Level 0: Stakeholder Engagement national, provincial, district and facility level | Buy-in for an integrated approach: facility level support is critical for success
Maturity Level 1: Deployment of IT Hardware Support | Coordination with provincial and district ICT departments
Maturity level 2: Site preparation, hardware integration and phased connectivity | Facility flow and patient flow optimized and network computing
Maturity Level 3: Implementation of HPRS System and Web-based District Health Information System Solution | Improve patient file retrieval and waiting time: efficient reporting because staff have more time for clinical services
Maturity level 4: Web based reporting and online data capture | Centralised routine data and therefore real-time data
“CHANGE MANAGEMENT!”

## Slide 9: Steps required before Implementation
Business Process Mapping of each facility
Redesign patient and data flow processes
  Patient Registration
  Patient Record Retrieval
  Patient Appointment
  Visit recording (PHC Headcount)
Rationalisation of Registers
Development and Implementation of a standardised filing system
  Alpha Numeric Filing Systems (ANFS)
  Identification of facility, patient and locating physical position of the patient record in the filing system

## Slide 10: Technical Requirements
Notes: Online and Offline Capability

## Slide 11: How was it implemented?
Between 2014 – 2015 HPRS was implemented as part of the NHI Pilot program in selected Districts and in 700 Facilities in South Africa to help refine the system for expansion and upscaling.
National managed the implementation with little or no support from Province or District
In Gauteng the City of Tshwane Metropolitan Municipality was selected
  76 Facilities Selected
  Admin Computers 254
  496 Consulting Computers

## Slide 12: Current Status in Gauteng
Chart: Facilities Implementing HPRS (21/04/2019)
| EKN | TSH | COJ | SED | WR | TOTAL
Total Number of Health Care Facilities | 104 | 87 | 130 | 42 | 55 | 418
Health Patient Registration System implemented (Website) | 63 | 51 | 58 | 38 | 47 | 257
Number of facilities capturing monthly | 15 | 49 | 50 | 42 | 39 | 195

## Slide 13: Current Status vs Population in Gauteng
Chart: Total Population
| EKN | TSH | COJ | SED | WR
Total Population in District | 3550039 | 3454751 | 5172937 | 982061 | 879799
Total Uninsured Population | 2670428 | 2401692 | 3880738 | 773424 | 674696
# Patients registed in HPRS | 958212 | 1914904 | 1061634 | 810329 | 399086
# Monthly Patient Visits in HPRS | 688786 | 2284841 | 446617 | 1446834 | 231793

## Slide 14: High Level Challenges
Lack of adoption by facilities due to lack of training and accountability (especially Metro’s)
Lack of communication between NDOH, Province, District and Facilities.
Connectivity!!!
Outdated ICT Infrastructure, network and hardware
Lack of ICT support and maintenance (No Asset Management)
Facility Infrastructure: Filing systems, security and access control (Missing files!)
Data and File Flows (Waiting times!)
New Files!!
Lack of Archiving systems for disposal and destruction of archiving at facility and district level
Lack of dedicated resources – site level “HPRS Champions”
Lack of Policies, SOP’s, SLA’s, guidelines and tools
No collaborative platform
Data Quality (Incorrect performance reporting)
On-site administrative support
Lack of dedicated Filing Clerks for sustainability
Parallel Systems: RX Solutions, Medimass, eHealth and Sync
Still to be piloted in Hospitals

## Slide 15: Gauteng Specific Challenges
ICT Infrastructure | Computers delivered in 2015/ 2016 (Outdated systems) Computers have been stolen, reallocated or are not in working order No Asset Management Virtual Machines have not been set-up
Connectivity | Current network do not support HPRS In some facilities data is stored locally and not synchronised If a facility has connectivity – data is captured centrally
Filing Systems | Patient files are still being filed according to old file plans (creating duplicate patient files). Infrastructure is not compliant (Lack of space, storage, data flow charts) Disposal of “Inactive” files not being done – No District Archives HPRN number is not unique New files are problematic
Resources | EWP’s are used (interns for 1 year) – no sustainability plan
Management and Support | Calls are logged for ICT issues but no response is received No support from District, Province or National Duplicates in System INTENSE data cleaning is required
Lack of Policies, SOP’s and Guidelines | Support documents available are the Technical Implementation and User Manual Audit General Findings that Site level SOP’s are needed No SLA’s
Change Management | No training records could be found No adoption of the system

## Slide 16: What is working?
Facilities with connectivity:
  HPRS computers connect to the central server (CSIR) and capture data.
  KT Motubatse have implemented the “Appointment Module” and will pilot it with the paper for one week.
  By using the ID number and being linked centrally they can identify patients registered at other facilities.
Files are being filed according to the HPRN number which makes retrieving simpler
Will eventually be linked to NHLS, TIER and other parallel systems.
The beginning of a Electronic Health Record

## Slide 17: Project Initiative
Background:
Previous experience shows that the implementation of Health Information Systems at facility level does not receive support from the Provincial Department of Health.
ICT Hardware Infrastructure, records management and Health Information Systems all form the foundation for providing good quality data!
Project Initiative:
Second a Technical Advisor in Health Information management to the Provincial Department of Health to support them in the implementation of health information management systems:
Provide support in the implementation of HPRS
Provide support in setting solid foundations in facilities with regards to Technology, HIS Resources and Records Management.
* Key criteria is to not do the work for them but to assist them in doing it to ensure sustainability.

## Slide 18: Key Measurements of Success
Dedicated Steering Committee lead by the Provincial team with a detailed “Terms of Reference”.
Project, Improvement and Action plans per facility
  Records Management
  HPRS
Performance measurement key indicators:
  # of Facilities with HPRS Implemented
  # of Facilities with consistent monthly visits in accordance with Head Count
  # of Facilities with reduced patient waiting times
  # of Facilities with newly implemented Filing systems
  # of Facilities sending records to an off-site archiving centre

## Slide 19: Methodology
Develop a well defined Steering Committee with Terms of Reference for accountability.
Define the Roles and Responsibilities for the eHealth, ICT and Records Management team at all levels in the DOH.
Research all the Health Information strategies, policies, SOP’s and guidelines, identify gaps and assist the teams in strengthening them.
Develop an implementation plan for the Province for the effective rollout of HPRS. (ICT, Filing and Records Management)
Assess the Records Management and Archiving processes across the Province and assist teams in implementing improvement plans per facility. (Problem and Solution based approach)
Provide mentoring and coaching to the Provincial Team (eHealth and Records Management) on health information management strategies.
Provide Technical Advise on new systems or data quality improvement tools.
Pilot the biometrics, bar code scanner and appointment scheduler in 3 pilot sites

## Slide 20: Progress to Date
HPRS Steering Committee developed with structured monthly district meetings with detailed minutes and action plans
ICT Systems Coordinators Roles and Responsibilities workshop conducted and new job descriptions developed. (Records Management in Progress.)
HPRS Dashboard with project mapping developed per district and per facility
ICT/ Filing Profiling Assessment developed and piloted in one facility. Building in REDCap for Rollout to ICT team’s in each District.
All Policies, SOP’s and guidelines reviewed
Started a central repository for document management and shared with the Provincial Team. This will be used to develop a collaborative platform
Providing mentoring and coaching to all levels of staff
Started with creating a “Records Management” mapping blueprint

## Slide 21: Problems to Date
ICT, eHealth, Records Management and Health Information Systems are in different departments.
Lack of communication and coordination between all levels
Provincial Records Manager moved to eGov. The current team are not involved in Patient Records and cannot support the archiving/ filing process at facility/ district Level
Provincial Teams supporting eHealth/ Records do not have computers/ laptops.
Lack of structured systems to manage and support facilities.
Different versions of policies and SOP’s across the Province
Changes in top level Directorates and new MEC may change the focus.
Access to HPRS data cannot be given to anyone outside of the DOH
Complete lack of data quality validation or verification plans
Provincial building burning down destroyed a lot of records and focus of Province is to move into a digitalised environment

## Slide 22: Next Steps
NATIONAL | PROVINCE | DISTRICT | FACILITY
Provide updated Policies and SOP’s | Upgrade all facilities to GBN Network | Complete ICT/ Filing Assessment Forms | Assess current filing systems, identify needs and possible solutions. Submit to District for approval
Provide HPRS “Train the Trainer” training. (Technical, End User and Management) | Install LTE in facilities with no GBN network | Analyse data and submit requirements to Province | Appoint dedicated Filing teams with a “Champion” to take accountability.
Allocate HPRS administrative rights to facility level “Champions” | Upgrade ICT Infrastructure across Province | Install new hardware and upgrade connectivity in facilities | Performance manage compliance to use of HPRS
Data De-duplication in HPRS | Develop and implement SLA’s | Identify HPRS/ Records Management Champions | Data Cleaning of HPRS data with Head Count book
HPRS New Version: Incorporate changes from Districts | Provide a system for management and support | Signed off MEMO for implementation in Metro facilities | Implement and maintain new filing systems
Develop SLA’s for all levels in the District | Develop a collaborative forum |  | Asset Management

## Slide 23: Assistance 
Gauteng Network Architecture
Filing System Infrastructure in Facilities
Tracking System for File Management
Pilot full HPRS system usage:
  Biometrics
  Bar Code Labels
  Appointment System
Archiving platform for the Province – per District
Collaborative Platform
ICT Support