## Instructions
UNDER DEVELOPMENT
Purpose: | The purpose of this tool is to notify partners of the needs of each facility towards achieving 90-90-90 targets. Recommendations will be compiled into a master spreadsheet and shared with partners on a weekly basis for their feedback and planned response to action items.
Instructions: | Site leads should update their spreadsheet for each facility visit and upload onto the S drive by the following Monday, COB. TDY teams who do not have S Drive access should email their spreadsheet to Reshma Supersad (ouj1@cdc.gov).
COLUMN | RESPONDER | DIRECTIONS | ADDITIONAL NOTES
A - F | CDC Site Lead | Site Leads should fill out all facility information using drop-down options. | Re-enter data for this section for each new row created.
G | CDC Site Lead | Enter Date of when Key Finding was identified. Date should be formatted as "DD-Mon-YY" | Use the same date for a Key Finding until it is resolved.
H | CDC Site Lead | Create a unique identifier for each Key Finding using the first 3 letters of facility name, first 3 letters of PSNU, abbreviation of partner name (Aurum: AHR, Health Systems Trust: HST, TB HIV Care: THC, Wits Reproductive Health & HIV Institute: WRHI), and 3 digits (beginning with 001). | The unique identifier will be the same for a key finding until the issue/challenge is resolved. For example, for Chatsworth Township Centre Clinic in eThekwini Metropolitan Municipality and supported by HST, the unique identifiers would be CHA-ETH-HST-001, CHA-ETH-HST-002, CHA-ETH-HST-003, and so forth.
I | CDC Site Lead | Categorize each Key Finding using the following drop-down options: 1st 90, 2nd 90, 3rd 90, Cross-cutting, Data Quality, Filing Issues, HPRS Implementation, HRH, Infrastructure, Lab, Resources, Other. | Definitions: 1st 90, 90% of all PLWH will know HIV status; 2nd 90, 90% of all diagnosed with HIV infection will receive ART; 3rd 90, 90% all on ART will have viral suppression; HRH, human resources.
J | CDC Site Lead | Concisely describe each Key Finding. Create new row for each Key Finding. | Key findings are any issues or challenges noted in a facility. Detailed explanations can be documented in "CDC Internal Notes" column.
K | CDC Site Lead | Select status of issue ("Key Finding") from drop-down options: Active, On Hold, Resolved | Only issues ("Key Finding") marked as "Active" will be added to master spreadsheet and shared with partners.
L | CDC Site Lead | Enter date of CDC Site Visit whenever a Key Finding is addressed. Date should be formatted as "DD-Mon-YY"
M | CDC Site Lead | Conscisely describe recommendations for each Key Finding. If there are multiple recommendations for a single Key Finding, enter each recommendation on a separate row.
N | CDC Site Lead | Enter any updates for a recommendation.
O | CDC Site Lead | Select level of urgency for a recommenation from the drop-down options: High, Medium, Low.
P | CDC Site Lead | Select follow-up organization for addressing a recommendation from drop-down options: District, DSP, Municipality, NDOH, PDOH. | Definitions: DSP, district support partner; NDOH, National Department of Health; PDOH, provincial department of health. NOTE: If a recommendation is for the facility manager, please select DSP to have them follow-up with the manager.
Q | Partner | Partner will enter date of response to CDC recommendation. Date should be formatted as "DD-Mon-YY"
R | Partner | Partner will enter response and plan to action to address CDC recommendation.
S | CDC Site Lead | Site leads can use this space for internal notes, including detailed explanations of key findings, name of team member who conducted a site visit, etc. | This section will not be shared on master spreadsheet sent to partners.
NOTE: A master spreadsheet with responses from partners will be added to the S Drive (here: ) and shared by email to site leads.

## Updated Template v1
CDC will fill out All YELLOW | [5 empty] | CDC will fill out all ORANGE |  |  |  |  | CDC will fill out all BLUE |  |  |  |  | Follow-Up Organization will fill out all GREEN |  | CDC can fill out PURPLE
Facility Name | SNU1 | PSNU | Agency | Partner | Site Lead | Date Identified, DD-Mon-YY | Unique Identifier (see instructions) | Category | Key Findings | Issue Status | Date of CDC Site Visit, DD-Mon-YY | CDC Recommendation | Update | Level of Urgency | Follow-up Organization (NDOH, PDOH, District, or DSP) | Date of Organization Response/ Actions, DD-Mon-YY | Organization Response/Actions | CDC Internal Notes

## Example
CDC will fill out All YELLOW | [5 empty] | CDC will fill out all ORANGE |  |  |  |  | CDC will fill out all BLUE |  |  |  |  | Follow-Up Organization will fill out all GREEN |  | CDC can fill out PURPLE
Facility Name | SNU1 | PSNU | Agency | Partner | Site Lead | Date Identified, DD-Mon-YY | Unique Identifier (see instructions) | Category | Key Findings | Issue Status | Date of CDC Site Visit, DD-Mon-YY | CDC Recommendation | Update | Level of Urgency | Follow-up Organization (NDOH, PDOH, District, or DSP) | Date of Organization Response/ Actions, DD-Mon-YY | Organization Response/Actions | CDC Internal Notes
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-06 | Hire 3 additional data capturers | None - key finding noted this visit | HIGH | DSP | 2019-05-09 | Will work to hire additional capturers
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-08 | Hire 3 additional data capturers | Interviews for capturers are being scheduled. | HIGH | DSP | 2019-05-10 | Interviews took place; 2 hired
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-09 | Hire 1 additional data capturers | Two data capturers hired. | MEDIUM | DSP | 2019-05-11 | Working to hire 1 more
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-10 | Train all data capturers in correct entry | All 3 data captures are hired. | MEDIUM | DSP | 2019-05-12 | Will organize in-house training
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-11 | Train all data capturers in correct entry | Training scheduled. | MEDIUM | DSP | 2019-05-13 | Had in-house training
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-12 | Assess file flow | File backlog continues. | MEDIUM | DSP | 2019-05-14 | Will work with facility to assess flow
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-13 | Finalize file flow | File flow assessment underway. | MEDIUM | DSP | 2019-05-15 | Will determine optimum flow and create diagram
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-14 | Finalize file flow | File flow diagram under development. | MEDIUM | DSP | 2019-05-16 | Will share and post diagram in file clerk room
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-001 | Filing Issues | Backlog of files for entry into TIER | Resolved | 2019-05-23 | None - issue resolved. | Resolved |  | DSP
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-002 | Data Quality | Data errors are frequent | Active | 2019-05-06 | Develop SOP for data entry | None - key finding noted this visit | HIGH | DSP | 2019-05-16 | Will develop SOP
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-06 | CHA-ETH-HST-002 | Data Quality | Data errors are frequent | Active | 2019-05-23 | Train data capturers | SOP developed. | HIGH | DSP
kz Chatsworth Township Centre Clinic | kz KwaZulu-Natal Province | kz eThekwini Metropolitan Municipality | HHS/CDC | Health Systems Trust | Adeboye Adelekan | 2019-05-20 | CHA-ETH-HST-003 | Resources | No private area for HIV counseling | On Hold | 2019-05-20 | Park home is needed to address space issue | None - key finding noted this visit | LOW | DSP

## Picklists
Picklists | Facility Name | SNU1 | PSNU | Agency | Partner | Site Lead | Issue Status | Follow-up Organization (NDOH, PDOH, District, or DSP) | Category | Level of Urgency
| ec Butterworth Gateway Clinic | ec Eastern Cape Province | ec Amathole District Municipality | HHS/CDC | Aurum Health Research | Adeboye Adelekan | Active | District | 1st 90 | HIGH
| ec Civic Centre Clinic (Mthatha) | gp Gauteng Province | ec Chris Hani District Municipality |  | Health Systems Trust | Anne Ochieng | Resolved | DSP | 2nd 90 | MEDIUM
| ec Flagstaff Clinic | kz KwaZulu-Natal Province | ec Oliver Tambo District Municipality |  | TB/HIV Care | Carolyn Hall | On Hold | Municipality | 3rd 90 | LOW
| ec Holy Cross Gateway Clinic | nw North West Province | gp City of Tshwane Metropolitan Municipality |  | Wits Reproductive Health& HIV Institute | Cobus Olivier |  | NDOH | Cross-cutting
| ec Idutywa Village CHC |  | gp Ekurhuleni Metropolitan Municipality |  |  | Diane Morof |  | PDOH | Data Quality
| ec Lusikisiki Village Clinic (Qaukeni) |  | kz eThekwini Metropolitan Municipality |  |  | Gugu Mona |  |  | Filing Issues
| ec Mhlakulo CHC |  | kz uMgungundlovu District Municipality |  |  | Gurpreet Kindra |  |  | HPRS Implementation
| ec Mqanduli CHC |  | kz Uthukela District Municipality |  |  | Helen Savva |  |  | HRH
| ec Mthatha Gateway Clinic |  | kz Zululand District Municipality |  |  | Hloni Mabuza |  |  | Infrastructure
| ec Ngangelizwe CHC |  | nw Bojanala Platinum District Municipality |  |  | Karidia Diallo |  |  | Lab
| ec Nozuko Clinic |  | nw Dr Kenneth Kaunda District Municipality |  |  | Leigh Berrie |  |  | Other
| ec Nqamakwe CHC |  | nw Dr Ruth Segomotsi Mompati |  |  | Lerato Lesole |  |  | Resources
| ec Ntapane Clinic |  | nw Ngaka Modiri Molema |  |  | Linnetie Mugore
| ec Port St Johns CHC |  |  |  |  | Maria Insua
| ec Qumbu CHC |  |  |  |  | Marissa Courey
| ec St Elizabeth's Gateway Clinic |  |  |  |  | Mary Mogoshoa
| ec Stanford Terrace Clinic |  |  |  |  | Meredith McMorrow
| ec Tombo CHC |  |  |  |  | Monica Patton
| ec Tsolo Clinic |  |  |  |  | Motlatsi Diale
| ec Willowvale CHC |  |  |  |  | Mpume Khanyile
| ec Xhora CHC |  |  |  |  | Nkosi Mpofu
| gp Andries Raditsela Clinic |  |  |  |  | Pelagia Murangandi
| gp Barcelona Clinic |  |  |  |  | Philippe Chiliade
| gp Boikhutsong Clinic |  |  |  |  | Refilwe Sello
| gp Boksburg Civic Centre Clinic |  |  |  |  | Romel Lacson
| gp Boksburg North Clinic |  |  |  |  | Sibo Dladla
| gp Bonaero Park Clinic |  |  |  |  | Thembakazi Matsheke
| gp Chief Albert Luthuli Clinic |  |  |  |  | TDY Team 1
| gp Crystal Park Clinic |  |  |  |  | TDY Team 2
| gp Dark City CHC |  |  |  |  | TDY team 3
| gp Daveyton East Clinic |  |  |  |  | TDY team 4
| gp Daveyton Main CDC |  |  |  |  | TDY team 5
| gp Dawn Park Clinic |  |  |  |  | TDY team 6
| gp Dresser Clinic |  |  |  |  | TDY team 7
gp Dukathole Clinic
gp Endayeni Clinic
gp Erin Clinic
gp Esangweni CHC
gp Ethafeni Clinic
gp FF Ribeiro Clinic
gp First Avenue Clinic
gp Germiston City Clinic
gp Goba Clinic
gp Hercules Clinic
gp Itireleng (Region B) Clinic
gp Jabulane Dumane CHC
gp Katlehong North Clinic
gp Kempton Park Civic Centre Clinic
gp Kemston Clinic
gp Kgabo CHC
gp Khumalo Clinic
gp KT Motubatse Clinic
gp Kwa-Thema CHC
gp Laudium CHC
gp Leondale Clinic
gp Lethabong Clinic
gp Lyttelton Clinic
gp Maria Rantho Clinic
gp Mary Moodley Memorial CDC
gp Moleleki Clinic
gp Nokuthela Ngwenya CHC
gp Olifantsfontein Clinic
gp Palmridge Clinic
gp Payneville Clinic
gp Phedisong 1 Clinic
gp Phedisong 4 CHC
gp Phenduka Clinic
gp Phillip Moyo CHC
gp Phola Park CHC
gp Phomolong Clinic
gp Ramokonopi CHC
gp Rondebult Clinic
gp Sedilega Clinic
gp Soshanguve 2 Clinic
gp Soshanguve Block JJ Clinic
gp Soshanguve Block TT Clinic
gp Soshanguve Block X Clinic
gp Soshanguve CHC
gp Spartan Clinic
gp Stanza Bopape CHC
gp Stanza Bopape II Clinic
gp Tamaho Clinic
gp Temba CHC
gp Tembisa Health Clinic
gp Tembisa Main Clinic
gp Tsakane Clinic
gp Vosloorus Poly Clinic
gp Wannenburg Clinic
gp Winnie Mandela Clinic
kz Amanzimtoti Clinic
kz Appelsbosch Gateway Clinic
kz Azalea Clinic
kz Bergville Clinic
kz Besters Clinic
kz Bhekuzulu Clinic
kz Caluza Clinic
kz Caneside Clinic
kz Chatsworth Township Centre Clinic
kz Chesterville Clinic
kz Clare Estate Clinic
kz Connor Street Clinic
kz Cramond Clinic
kz eDumbe CHC
kz Emmaus Gateway Clinic
kz Ezakheni 2 Clinic
kz Glen Earle Clinic
kz Gomane Clinic
kz Hambanathi Clinic
kz Hlobane Clinic
kz Howick Clinic
kz Illovu Clinic
kz Impilwenhle Clinic
kz Inanda Seminary Clinic
kz Injisuthi Clinic
kz Isipingo Clinic
kz Kingsburgh Clinic
kz Klaarwater Clinic
kz KwaMashu B Clinic
kz Lamontville Clinic
kz Lancers Road Clinic
kz Luganda Clinic
kz Mafakathini Clinic
kz Mason Street Clinic
kz Mooi River Clinic
kz Mpola Clinic
kz Mpophomeni Clinic
kz Mpumuza Clinic
kz Mzamo Clinic
kz Nagina Clinic
kz Ncotshane Clinic
kz Ndaleni Clinic
kz New Germany Clinic
kz Newlands West Clinic
kz Ntabamhlope Clinic
kz Ottawa Clinic
kz Overport Clinic
kz Pata Clinic
kz Pinetown Clinic
kz Pongola Clinic
kz Prince Zulu Communicable Diseases Centre Clinic
kz Queen Nolonolo Clinic
kz Redcliffe Clinic
kz Redhill Clinic
kz Reservoir Hills Clinic
kz Richmond Clinic
kz Savannah Park Clinic
kz Shallcross Clinic
kz Sinathing Clinic
kz Songonzima Clinic
kz St Chads CHC
kz Sydenham Heights Clinic
kz Taylors Halt Clinic
kz Tshelimnyama Clinic
kz Ulundi A Clinic
kz Umlazi G Clinic
kz Umlazi N Clinic
kz Verulam Clinic
kz Walton Clinic
kz Waterfall Clinic
kz Waterloo Clinic
kz Wembezi Clinic
kz Willowfountain Clinic
kz Wyebank Clinic
nw Bafokeng CHC
nw Bapong CHC
nw Boikhutso Clinic
nw Boitekong Clinic
nw Grace Mokgomo CHC
nw Hebron Clinic
nw Jouberton CHC
nw Letlhabile CHC
nw Lonely Park Clinic
nw Mogwase CHC
nw Montshia Stadt CHC
nw Park Street Clinic
nw Potchefstroom Clinic
nw Tlhabane CHC
nw Unit 9 CHC